## 26 Adopted
ADOPTED Johnson County Secondary Roads Department 5-Year Construction Program
with the Maintenance Rehabilitation Program (MRP) shaded in purple
Adopted by Johnson County Board of Supervisors on April 30, 2026
Created: December 15, 2025 Last Revised: April 1, 2026
| 5YR ID | OLD | TPMS ID | Construction | Project Name and Number | Cost Est. | AADT | Length
FY26/27 | 26A |  |  | 2026 | F67 (540th Street SW) - County Line to Hwy 1 | 6510000 | 990 / 830 | 6.0 mi. | $15.885M = '26 Construction
|  | 22B | 35351 |  | FM-C052(130)--55-52 | FM
Pavement Restoration
| 26B |  |  | 2026 | F62 (500th Street SW) - Angle Rd SW to Hwy 1 | 1500000 | 2010 | 1.3 mi.
|  | 22F | 35354 |  | LFM-500th--7X-52 | Local
Pavement Restoration
| 26C |  |  | 2026 | R-19-2, Maier Avenue SW over Picayune Creek | 450000 | 10 | 0.1 mi.
|  | 22H | 37817 |  | L-R-19-2--73-52 | Local
Bridge Replacement
| 26D |  |  | 2026 | M-18-1, Greencastle Ave SW over Old Woman's Creek | 350000 | 45 | 0.1 mi.
|  | NEW | 52833 |  | L-M-18-1--73-52 | Local
Bridge Replacement
| 26E |  |  | 2026 | X14 (Wapsi Ave SE) - Hwy 22 to 520th St | 3500000 | 2020 | 4.0 mi.
|  | 22I | 45218 |  | STP-S-C052(132)--5E-52 | $2,800,000 FA
[5 empty] | Pavement Restoration | $700,000 FM
| 26F |  |  | 2026 | P-34-2, Derby Ave SW over Schaffer Creek | 500000 | 60 | 0.1 mi.
|  | 23E | 45220 |  | L-P-34-2--73-52 | Local
Bridge Replacement
| 26G |  |  | 2026 | F8W (Morse Road NE) Ph 1 of 2 - Hwy 1 to Wapsi Ave NE | 1200000 | 1220 | 1.6 mi.
|  | 23C | 52392 |  | LFM-Morse-1--7X-52 | Local
Pavement Restoration
| 26H |  |  | 2026 | O-27-3, Eagle Ave SW over Bradley Creek | 500000 | 30 | 0.2 mi.
[5 empty] | L-O-27-3--73-52 | Local
Bridge Replacement
| 26I |  |  | 2026 | P-12-6, Angle Road SW over branch of Old Mans Creek | 150000 | 90 | 0.1 mi.
[5 empty] | L-P-12-6--73-52 | Local
Box Culvert
| 26J |  |  | 2026 | Club Road NE - Shueyville to Linn County | 625000 | 1340 | 0.5 mi.
|  | NEW | 52856 |  | LFM-Club--7X-52 | 2022 Bond
Pavement Rehabilitation
| 26K NEW |  |  | 2026 | I-9-4, F8W (Morse Road NE) over Rapid Creek | 600000 | 1220 | 0.2 mi.
[5 empty] | LFM-I-9-4--7X-52 | Local
Bridge Replacement
| M26-1 |  |  | 2026 | Taft Avenue SE - F46 (American Legion Rd SE) to 420th St SE | 40000 | 260 | 1.3 mi. | $310k = '26 MRP
|  | M22-3 | MRP
Grade, Macadam Stone Base, Choke Stone Surface
| M26-2 |  |  | 2026 | Taft Avenue SE - F46 (American Legion Rd SE) to 420th St SE | 80000 | 260 | 1.3 mi.
|  | M22-5 | MRP
Double Seal Coat Surface
| M26-3 |  |  | 2026 | Johnson Washington Road - East of Hwy1 to Hazelwood Ave SW | 40000 | 280 | 1.0 mi.
|  | M23-3 | MRP
Grade, Macadam Stone Base, Choke Stone Surface
| M26-4 |  |  | 2026 | F46 (IWV Road SW) - W38 (Blackhawk Ave SW) to Cosgrove Rd SW | 150000 | 480 | 3.5 mi.
|  | M23-4 | MRP
Slurry Seal
FY27/28 | 27A |  |  | 2027 | Dillon's Furrow Road NE & F28 (210th St NE) - Hwy 1 to Hwy 1 & Intersections | 1510000 | 35 DFR 9000 / 210 Hwy 1 - 210th | 1.2 mi. | $21.495M = '27 Construction
[5 empty] | L-DFR--73-52 | $382,500 Local
[5 empty] | Grade, Macadam Stone Base, Choke Stone Surface, Intersection Improvements | $1,127,500 Dev. Agreement
| 27B |  |  | 2027 | W6E (Ely Road NE) Phase 5 - F12 (140th St NE) to 2000 ft. s. of Linn County | 4800000 | 4610 / 4160 | 2.07 mi.
|  | 22D | 36526 |  | LFM-Ely--7X-52 | Local
Reconstruction with Flood Mitigation
| 27C |  |  | 2027 | F8W (Morse Road NE) Ph 2 of 2 - Wapsi Ave NE to Cedar County | 3750000 | 1220 / 820 | 4.8 mi.
|  | 23B | 52391 |  | LFM-Morse-2--7X-52 | Local
Pavement Restoration
| 27D |  |  | 2027 | F62 (500th St SW) - W64 (Oak Crest Hill Rd) west 2.1 mi. to end of ex. HMA | 2000000 | 590 | 2.1 mi.
|  | 23A | 39062 |  | STP-S-C052( )--5E-52 | $1,600,000 FA
[5 empty] | Pavement Rehabilitation | $400,000 FM
| 27E |  |  | 2027 | X14 (Utah Ave SE) - F62 (520th St SE) to Hwy 6 | 3500000 | 1290 | 3.5 mi.
|  | 23B | 52391 |  | FM-C052( )--55-52 | FM
Pavement Rehabilitation
| 27F |  |  | 2027 | W66 (Dubuque Street NE) Roundabout - at Rustic Ridge Rd NE | 2665000 | 4930 / 5900 / 800 | 0.3 mi.
|  | NEW | 52856 |  | STP-S-C052( )--5E-52 | $2,132,000 FA
[5 empty] | Reconstruction | $266,500 FM / $266,500 Other
| 27G |  |  | 2027 | F12 (120th St NE) Ph 1 of 2 - Shueyville to Hickory Hollow Rd NE | 2270000 | 2210 | 1.5 mi.
|  | 23B | 52391 |  | LFM-120-E1--7X-52 | $1.925M 2022 Bond
[5 empty] | Pavement Rehabilitation | $345k Local
| 27H NEW |  |  | 2027 | H-31-2, Rapid Creek Rd NE over Rapid Creek | 1000000 | 490 | 0.2 mi.
[5 empty] | LFM-H-31-2--7X-52 | Local
Bridge Replacement
| M27-1 |  |  | 2027 | Wapsi Ave NE/SE - F44 (Herbert Hoover Hwy NE) to F46 (American Legion Rd SE) | 120000 | 220 / 140 / 80 | 2.4 mi. | $375k = '27 MRP
|  | M22-3 | MRP
Double Seal Coat Surface
| M27-2 |  |  | 2027 | 180th Street NE - Solon to Utah Ave NE | 125000 | 440 | 2.5 mi.
|  | M23-2 | MRP
Double Seal Coat Surface
| M27-3 |  |  | 2027 | Rohret Road SW and Jasper Avenue SW | 80000 | 270 / 210 / 120 | 0.1 mi.
Intersection Regrade
| M27-4 |  |  | 2027 | Racine Avenue NE and Jordan Creek Road NE | 50000 | 180 / 160 / 120 | 0.1 mi.
|  | M24-2 | MRP
Intersection Realignment
FY28/29 | 28A |  |  | 2028 | F12 (120th Street NE) Ph 2 of 2 - Hickory Hollow Rd NE to W6E (Ely Rd NE) | 3100000 | 1890 | 2.5 mi. | $12.075M = '28 Construction
|  | 24A | 45219 |  | FM-C052( )--55-52 | FM
Pavement Rehabilitation
| 28B |  |  | 2028 | Lower Old Highway 6 Road NW - Hwy 6 to Hwy 6 | 1125000 | 500 | 1.5 mi.
|  | 24D | 45222 |  | L-Lower_Old_6--73-52 | Local
Pavement Restoration
| 28C |  |  | 2028 | F46 (IWV Road SW) Ph 1 of 3 - Greencastle Ave SW to Ivy Ave SW | 5000000 | 1050 | 2.1 mi.
|  | NEW | 52857 |  | LFM-IWV-W1--7X-52 | Local
Reconstruction
| 28D |  |  | 2028 | P-20-1, 520th St SW over Deer Creek | 500000 | 35 | 0.2 mi.
|  | 23F | 37819 |  | L-P-20-1--73-52 | Local
Bridge Replacement
| 28E |  |  | 2028 | I-21-5, Rapid Creek Road NE over branch of Rapid Creek | 850000 | 130 | 0.2 mi.
[5 empty] | BROS-C052( )--5F-52 | HBP
Bridge Replacement
| 28F NEW |  |  | 2028 | S-23-2, F62 (520th Street SE) over Iowa River | 1500000 | 2060 | 0.1 mi.
[5 empty] | BHS-C052( )--63-52 | HBP
Bridge Deck Replacement
| M28-1 |  |  | 2028 | Maier Ave SW - Hwy 1 to 480' south of Rohret Rd SW | 40000 | 230 | 1.2 mi. | $220k = '28 MRP
|  | NEW | MRP
Grade, Macadam Stone Base, Choke Stone Surface
| M28-2 |  |  | 2028 | James Ave NW and Swan Lake Rd NW - W60 (Hwy 965 NE) to F28 (250th St NW) | 100000 | 170 / 100 | 2.9 mi.
Grade, Macadam Stone Base, Choke Stone Surface
| M28-3 |  |  | 2028 | W64 (Oak Crest Hill Road SE) - Washington County Line to F50 (Old Hwy 218 NE) | 80000 | 2330 / 1530 | 7.4 mi.
PCC Patching
FY29/30 | 29A |  |  | 2029 | W38 (Blackhawk Ave NW/SW) - F46 (IWV Rd SW) to Oxford | 4000000 | 1450 / 1200 | 4.6 mi. | $9.000M = '29 Construction
|  | 24C | 39063 |  | FM-C052( )--55-52 | FM
Pavement Restoration
| 29B |  |  | 2029 | I-20-2, Dingleberry Road NE over Rapid Creek | 1000000 | 390 | 0.2 mi.
|  | 25A | 47293 |  | BROS-C052( )--8J-52 | HBP
Bridge Replacement
| 29C |  |  | 2029 | F46 (IWV Road SW) Ph 2 of 3 - Cosgrove Rd SW to Greencastle Ave SW | 2500000 | 1050 | 1.0 mi.
|  | NEW | 52858 |  | LFM-IWV-W2--7X-52 | Local
Reconstruction
| 29D NEW |  |  | 2029 | Bridge Replacement Bundle 2029, F62 (520th St SE) | 1500000 | 880 | 0.4 mi
[5 empty] | LFM-BRDG-29--7X-52 | Local
(S-20-2 & S-24-3)
FY30/31 | 30A |  |  | 2030 | F52 (Black Diamond Road SW) - Cosgrove Rd SW to 1000' e. of 450th St SW | 4000000 | 970 / 670 | 4.6 mi. | $5.250M = '30 Construction
|  | 26A | 52394 |  | FM-C052( )--55-52 | FM
Pavement Restoration
| 30B NEW |  |  | 2030 | U-30-4, W66 (670th St SE) over Prairie Creek | 500000 | 100 | 0.2 mi.
|  | 26D | 52396 |  | LFM-U-30-4--7X-52 | Local
Bridge Replacement
| 30C NEW |  |  | 2030 | A-22-1, 160th St NE over branch of Mill Creek | 500000 | 60 | 0.2 mi.
[5 empty] | L-A-22-1--73-52 | Local
Bridge Replacement
| 30D NEW |  |  | 2030 | J-2-1, 340th St NE over unnamed stream | 250000 | 50 | 0.2 mi.
|  | NEW | 52834 |  | L-J-2-1--73-52 | Local
Box Culvert
FY22 Bonding total $2,550,000 for F12 (120th Street NE) and Club Road NE